## How to use
Accessibility audit workbook
A workbook the team works in — not a report they read once.
The idea
An audit's value is decided by its format. A PDF is read once and ages while the product
changes. This workbook is the working surface of the remediation: the team fixes, verifies,
and closes findings inside it, and progress is computed — never typed — so it can't lie.
The five sheets
Findings register — the only sheet where work happens. One row per issue.
Evidence — screenshots, assistive tech, reproduction steps, by finding ID.
Systemic layer — the recurring causes behind clusters, and the rule that stops each recurring.
Dashboard — live counts by status, team, and severity. Read-only, all formulas.
Scope & method — what was tested, with what, when, against which target, and what was excluded.
Who works where
Auditor / researcher — builds the workbook, writes findings at the right granularity, owns the structure.
Developers — pick up findings by component, fix, move to Fixed, then to Verified after retest.
Content — owns copy, alt-text intent, link text, reading order in content.
Design — owns contrast, focus order, target size, and component-level (systemic) fixes.
Stakeholder — reads the Dashboard. Never edits the register.
The rule that keeps it honest
Status separates Fixed (made) from Verified (retested with assistive tech). The Dashboard
shows both. The gap between them is where accessibility programmes quietly fail.
Stakeholder question for every status meeting: how many findings are Verified, not just Fixed?
Expect to modify this
The sheets, columns, and status vocabulary are a sensible default, not a rule. If your team works in Jira, Azure DevOps, or Asana, export the register into your tracker and keep the systemic layer and dashboard here. Track at template level where failures are systemic rather than one row per instance. Bend it to your environment — adapting it is part of the work.
About this sheet
Created by Alessandro Zulberti at alessandrozulberti.com. It's a teaching tool, not a finished product — adapt it to your own catalogue, tooling, and team. Shared for others to use and modify; attribution appreciated if you build on it.
v1.0 · June 2026

## Findings register
Findings register
One row per issue — never per criterion. Everything here is filterable.
ID | Page / location | Component | What fails | WCAG criterion | Severity | User impact (plain) | Owning team | Status | Systemic? (link) | Notes
F-001 | Product listing | Product card image | Decorative product images announced as 'image' | 1.1.1 | Serious | Screen reader users hear 'image' with no product name on every card | Content | In progress | S-01 | Covered by alt-text grammar
F-002 | Checkout step 2 | Card number field | Input has no programmatic label | 3.3.2 | Blocker | Screen reader users cannot tell which field is which | Engineering | Fixed |  | Awaiting retest
F-003 | Global header | Search toggle | Focus not visible on keyboard navigation | 2.4.7 | Serious | Keyboard users lose track of where they are | Design | Verified | S-02 | Token-level fix applied
F-004 | PDF: size guide | Whole document | Untagged PDF, no reading order | 1.3.1 | Moderate | Reading order is unpredictable in a screen reader | Content | Open |  | Candidate for web page
Note on F4: A defined scale, not adjectives chosen ad hoc. Blocker = task cannot be completed with assistive tech. Serious = major barrier with a workaround. Moderate = friction. Minor = polish.
Note on I4: Open / In progress / Fixed (change made) / Verified (retested with assistive tech) / Accepted (a known limitation, consciously signed off) / Won't fix. The gap between Fixed and Verified is where programmes fail — keep them distinct.
Note on J4: If this finding is one instance of a recurring cause, put the systemic ID here (e.g. S-01) so it links to the Systemic layer sheet. Closing the systemic cause is what stops it regenerating.

## Evidence
Evidence
Written once, read under challenge. Each row must settle 'is this really a failure?' on its own.
Finding ID | Screenshot / file ref | Assistive tech used | Steps to reproduce | Expected | Actual

## Systemic layer
Systemic layer
The recurring causes behind clusters of findings — and the rule that stops each one regenerating.
Systemic ID | Pattern / cause | Findings it explains | Root fix (rule, not instance) | Owning team | Status
S-01 | Product images carry meaning but alt text is generic or absent | 1 | Apply a token grammar at the pipeline, so alt text is generated to a controlled vocabulary and audited at the rule level | Content | In progress
S-02 | Focus state not defined as a design token; missing across interactive components | 1 | Define a single focus-visible token in the design system; every component inherits it | Design | Verified

## Dashboard
Dashboard
Live from the Findings register. Nothing here is typed by hand.
By status |  | By severity
Total findings | 4 | Blocker | 1
Open | 1 | Serious | 2
In progress | 1 | Moderate | 1
Fixed | 1 | Minor | 0
Verified | 1
Accepted (known limitation) | 0
Won't fix | 0 | By owning team
|  | Engineering | 1
|  | Content | 2
|  | Design | 1
Verified, not just fixed |  | Research | 0
Fixed (change made, not retested) | 1 | Compliance | 0
Verified (retested with assistive tech) | 1
% of closed work that is actually verified | 50%
Blockers still open | 0

## Scope & method
Scope & method
For the reader two years from now — possibly a lawyer, possibly you.
Conformance target | WCAG 2.2 Level AA
Audit dates
Auditor / team
Pages / templates tested
Assistive technologies used | e.g. VoiceOver + Safari, NVDA + Firefox, keyboard-only
Browsers / devices
Sampling approach | e.g. one of each template type, plus highest-traffic pages
Explicitly excluded (and why)
Known limitations / assumptions
Re-audit trigger | e.g. next major release, or 6 months, whichever first